## Stakeholder Analysis
Stakeholder Assesment
Project Name : EcoEats Local Sourcing Initiative
Current state Desired state Place a C and D in a row for each stakeholder
Stakeholder | Interest | Influence Level (High/Med/Low) | Impact on Project
Restaurant Owners | Easy tagging tools, increased visibility/orders | High | Direct adoption drivers
Customers | Intuitive discovery features | High | User retention KPIs
Product Team | Alignment with roadmap | High | Feature prioritization
Operations Team | Minimal operational overhead | Med | Partnership management
Tech Team | Feasible tech stack | High | Development timelines
Marketing | Promotional content | Med | Launch success
Farmers | Accurate representation | Med | Data partnerships
Regulators | Compliance | Low | Legal risks

## Raci Matrix
RACI Matrix
Activity | Restaurant Owners | Customers | Product Team | Ops Team | Tech Team | Marketing | Farmers | Regulators
Define Requirements | C | C | R | A | I | I | C | I
Develop Features | I | I | A | C | R | I | I | I
Test & Validate | C | R (UAT) | A | C | R | I | C | I
Launch & Promote | I | I | A | R | I | R | C | I
(R = Responsible, A = Accountable, C = Consulted, I = Informed)